## Overview
Full Application v1.0.20 — User Acceptance Testing
Version: v1.0.20
Purpose | End-to-end validation of X-Checks Full Application v1.0.20 against the test_data\ files. Covers all five strategies (Collect Live X-Checks, X-Checks, Grouping By, Accounting Principles, Conditions) and Full Run, plus shared infrastructure: Processing Log, sensitivity labelling, stop/error handling.
Scope | All strategies in the production EXE, Full Run combined output, Processing Log content (output path + expected sensitivity label entries), colour coding on Comparison sheets, and error/stop handling. Collect Live X-Checks output (clipboard .txt) is noted but its data accuracy is out of scope for this plan.
Test executable | dist\X-Checks_v1.0.20.exe (production build).
Test data | All files are in test_data\ (repo root): • X-Checks pub: 20251205 EPM X-Checks - Original.xlsx (sheet: cross checks all) • X-Checks FIP: 20251205 FIP X-Checks - Original.txt • Grouping By FIP: VALFLDGR file with 12348 Data rows on sheet Sheet1.XLSX (sheet: Sheet1, 12348 rows) • Grouping By pub: 20260313 Cross Checks All.xlsx (sheet: cross checks all) • Mapping File: Mapping Table with 20 rows.txt (19 mapping entries) • AP pub: EPM X-Checks file with 3345 Data rows on sheet cross checks all.xlsx (sheet: cross checks all) • Known Exceptions: Known_Exception_List.xlsx (sheet: Known Exceptions, 2 rows)
Pre-conditions | 1) Tester is on Windows 10/11 with permission to run unsigned EXEs. 2) No test_data files are open in Excel before launching. 3) An output folder is available and writable. 4) Microsoft Information Protection client is installed (for sensitivity-label checks).
How to run a test | Read 'Steps', perform them on the running EXE, compare to 'Expected Result'. Enter the actual outcome in 'Actual Result' and set 'Pass / Fail'. If failed, add detail (screenshot path, error message, count observed).
Sign-off | Once all in-scope cases are Pass (or any Fail has been logged and triaged), complete the Sign-off sheet.

## Test Cases
Full Application v1.0.20 — UAT Test Cases
ID | Area | Precondition | Steps | Expected Result | Actual Result | Pass / Fail | Tester | Date
FA-01 | Launch & version | Production EXE present in dist\. | Double-click dist\X-Checks_v1.0.20.exe. | Splash screen appears showing 'X-Check Application v1.0.20 Loading...'. After ~2–5 s the task selector form opens with 'X-Check Application v1.0.20' in the title bar and UI label.
FA-02 | Launch & version | App is open at the task selector. | Confirm the version shown in the title bar and UI label. | Both display v1.0.20.
FA-03 | Task selector — dropdown | App is open at the task selector. | Open the task dropdown and count the entries. | 6 tasks are listed in this order: 1. Collect Live X-Checks 2. X-Checks 3. Grouping By 4. Accounting Principles 5. Conditions 6. Full Run
FA-04 | Task selector — navigation | App is open at the task selector. | Select each task in turn and confirm the file-selection form title. | Each task opens a correctly titled form: • Collect Live X-Checks → 'Collect Live X-Checks' • X-Checks → 'X-Check Files' • Grouping By → 'Grouping By Files' • Accounting Principles → 'Accounting Principles Files' • Conditions → 'Conditions Files' • Full Run → 'Full Run — All Strategies'
FA-05 | X-Checks — file fields | X-Checks task selected, file-selection form open. | Inspect the form fields. | Four fields present: 1. 'FIP File' (.txt) 2. 'X-Checks Publication File' (.xlsx, default sheet: 'cross checks all') 3. 'GCoA Publication File' (.xlsx, optional) 4. 'Known Exception List' (.xlsx, optional) Two experimental checkboxes: 'Apply Version Spanning Validation' and 'Apply Prior Year Balance Formula', both unchecked by default. 'Process only differences' checkbox is present and checked by default.
FA-06 | X-Checks — run (differences only) | X-Checks form open. | Set FIP File to '20251205 FIP X-Checks - Original.txt', X-Checks Publication File to '20251205 EPM X-Checks - Original.xlsx' (sheet: 'cross checks all'), no GCoA or Known Exception List. 'Process only differences' checked. Click Start. | Run completes. Progress log shows 664 X-Check entries extracted from the publication file and 650 matched in the FIP file.
FA-07 | X-Checks — output structure | FA-06 complete. Output workbook open. | Check the sheet tabs. | Workbook contains: 1. Comparison 2. Processing Log
FA-08 | X-Checks — comparison counts | FA-06 output, Comparison sheet open. | Count the rows and check the Formula Match column breakdown. | 653 rows total. Formula Match: 525 Match, 125 MisMatch, 3 Not Found.
FA-09 | X-Checks — Known Exception List | X-Checks form open. | Add 'Known_Exception_List.xlsx' (sheet: 'Known Exceptions') as the Known Exception List. Run with the same files as FA-06. | Run completes. Progress log references the Known Exception List. Rows matching the 2 exception entries are annotated in the output.
FA-10 | Grouping By — file fields | Grouping By task selected, file-selection form open. | Inspect the form fields. | Four fields present: 1. 'FIP File (ZQ9_VALFLDGR)' (.xlsx, default sheet: 'Sheet1') 2. 'X-Checks Publication File' (.xlsx, default sheet: 'cross checks all') 3. 'Mapping File' (.csv / .txt) 4. 'Known Exception List' (.xlsx, optional)
FA-11 | Grouping By — run | Grouping By form open. | Set FIP File (ZQ9_VALFLDGR) to 'VALFLDGR file with 12348 Data rows on sheet Sheet1.XLSX' (sheet: 'Sheet1'), X-Checks Publication File to '20260313 Cross Checks All.xlsx' (sheet: 'cross checks all'), Mapping File to 'Mapping Table with 20 rows.txt'. Click Start. | Run completes without error. Progress log shows: • FIP original loaded: 12348 rows • FIP processed (after mapping + filtering): 6776 rows • Mapping dictionary: 19 entries • EBX rows: 1499
FA-12 | Grouping By — output structure | FA-11 complete. Output workbook open. | Check the sheet tabs. | Workbook contains: 1. FIP - Original 2. FIP - Processed 3. EBX Processed 4. Comparison 5. Processing Log
FA-13 | Grouping By — colour coding | FA-11 output, Comparison sheet open. | Review the Result column. | 'Matched' rows have a green fill. 'Not in FIP' rows have an orange fill.
FA-14 | Accounting Principles — file fields | Accounting Principles task selected, file-selection form open. | Inspect the form fields. | Four fields present: 1. 'Validation Methods File' (.xlsx, sheet: 'Validation Methods') 2. 'X-Checks Publication File' (.xlsx, default sheet: 'cross checks all') 3. 'FIP File (VALMSG)' (.xlsx, sheet: 'FIP Methods Rules and Condition') 4. 'Known Exception List' (.xlsx, optional)
FA-15 | Accounting Principles — run | Accounting Principles form open. | Set X-Checks Publication File to 'EPM X-Checks file with 3345 Data rows on sheet cross checks all.xlsx' (sheet: 'cross checks all'), FIP File (VALMSG) and Validation Methods File as applicable. Click Start. | Run completes. Progress log confirms 3345 source rows in the publication file and processing of the FIP VALMSG file.
FA-16 | Accounting Principles — output structure | FA-15 complete. Output workbook open. | Check the sheet tabs. | Workbook contains: 1. Comparison 2. Working Sheet 3. FIP Data 4. Processing Log
FA-17 | Conditions — file fields | Conditions task selected, file-selection form open. | Inspect the form fields. | Three fields present: 1. 'X-Checks Publication File' (.xlsx, default sheet: 'cross checks all') 2. 'FIP File (ZQ9_VALMETH)' (.xlsx, default sheet: 'FIP Conditions') 3. 'Known Exception List' (.xlsx, optional) 'Process only differences' checkbox present and checked by default.
FA-18 | Conditions — colour coding | Any Conditions run complete. Output workbook open, Comparison sheet. | Review the Comparison column. | 'Matched' cells have a green fill. 'Not Matched' cells have a red fill.
FA-19 | Conditions — FIP Data column header | Any Conditions run complete. Output workbook open, FIP Data sheet. | Check the first column header. | First column is labelled 'Key (Concatenated)'.
FA-20 | Full Run — file fields | Full Run task selected, file-selection form open. | Count the file fields. | All unique fields from every strategy are merged into one form with no duplicates. Fields include FIP File, X-Checks Publication File, GCoA Publication File, FIP File (ZQ9_VALFLDGR), Mapping File, Validation Methods File, FIP File (VALMSG), FIP File (ZQ9_VALMETH), Known Exception List.
FA-21 | Full Run — run all strategies | Full Run form open. All test files loaded. | Set all required files using the test_data\ files and click Start. | All strategies run in sequence without error. Progress dialog shows steps for each strategy. Run completes with 'Processing complete'.
FA-22 | Full Run — combined output structure | FA-21 complete. Combined output workbook open. | Check all sheet tabs and their tab colours. | One workbook containing all strategy output sheets, each prefixed with the strategy name (e.g. 'XC — Comparison', 'GB — Comparison', etc.). Tabs are colour-coded by strategy group. A single 'Processing Log' sheet at the end contains the combined log.
FA-23 | Full Run — abort on strategy failure | Full Run form open. | Set an incorrect sheet name for one of the required files, then click Start. | The failing strategy logs a clear error. Full Run aborts immediately rather than continuing to the next strategy. 'Return to Form' is available.
FA-24 | Processing Log — content | Any completed run. Output workbook open, Processing Log sheet. | Review the log entries. | First entry shows v1.0.20. Log includes: files loaded, strategy-specific steps, output path, expected sensitivity label (Internal_Use_Only). All entries have a Timestamp, File, Step, and Count column.
FA-25 | Processing Log — output path entry | Any completed run. Processing Log sheet open. | Find the 'Output written to' entry. | An entry with File='Output' and Step starting 'Output written to:' is present in the log. This confirms the path was captured before the file was closed.
FA-26 | Processing Log — sensitivity label entry | Any completed run. Processing Log sheet open. | Find the sensitivity label entry. | An entry with File='Sensitivity' and Step='Expected label: Internal_Use_Only' is present. This records intent; the actual COM result is shown in the progress dialog only.
FA-27 | Sensitivity label — applied | Any completed run. Output file saved to disk. | Right-click the output .xlsx in Explorer → Properties → Details, or open in Excel and check the sensitivity bar. | File carries the 'Internal Use Only' Microsoft Information Protection label. Progress dialog shows 'Applied label: Internal_Use_Only'.
FA-28 | Stop / Return to Form | Any task started (click Start). | Click Stop during processing. | Processing halts cleanly. Progress dialog shows 'Processing halted by user'. 'Return to Form' button available. Clicking it reopens the file-selection form with previously chosen files pre-filled.
FA-29 | Error handling — wrong sheet name | Any task's file-selection form open. | Set the sheet name for any file to 'does_not_exist', then click Start. | Run aborts with a clear error identifying the missing sheet. App returns to form — does not crash or exit.
FA-30 | Error handling — missing required file | Any task's file-selection form open. | Click Start without selecting any required files. | Start does not begin processing. Form indicates which required fields are missing and does not crash.

## Sign-off
Full Application v1.0.20 — UAT Sign-off
Outcome | All in-scope cases passed (or any failure has been logged and triaged)?
Tester (name)
Tester (role)
Test start date
Test end date
Pass / Fail
Failures (count)
Notes
Approver (name)
Approver (role)
Approval date