## Overview
Fixture-Based UAT v1.0.59 — Test Plan
Version: v1.0.59 ¦ 14 Logic cases ¦ 25 Whole App cases
Purpose | Standalone UAT for X-Checks Full Application v1.0.59 using the minimal fixture files in test_data\fixtures\. Covers all strategies, UI, output structure, colour coding, sensitivity labelling, and error handling. Test cases are categorised: Logic (14 cases) — verifies row-level comparison output. Run after every code change to confirm strategy logic is correct. Whole App (25 cases) — verifies UI, structure, labelling, error handling. Run for full release sign-off.
Fixture files | All in test_data\fixtures\: xc_pub.xlsx — shared EBX publication (all strategies) fip_xc.txt — FIP X-Checks text fip_ZQ9_VALFLDGR.xlsx — FIP Grouping By mapping.txt — Grouping By mapping validation_methods.xlsx — AP Validation Methods (real reference file) fip_ZQ9_VALMSG.xlsx — FIP AP (raw ZQ9_VALMSG) fip_ZQ9_VALMETH.xlsx — FIP Conditions (raw ZQ9_VALMETH) Regenerate (except validation_methods.xlsx) with: python test_data/generate_test_fixtures.py
Test executable | dist\X-Checks_FullRun_1.0.59.exe
Pre-conditions | 1) EXE present in dist\. 2) No fixture files open in Excel. 3) An output folder is available and writable. 4) MIP client installed (for sensitivity-label checks). 5) 'Process only differences' unchecked unless the test case specifies otherwise.

## Test Cases
Fixture-Based UAT v1.0.59 — Test Cases
Test Type: Logic = verify comparison output logic Whole App = verify UI, structure, labelling, error handling
ID | Area | Test Type | Files / Setup | Steps | Expected Result | Actual Result | Pass / Fail | Tester | Date
FX-01 | Launch & version | Whole App | Production EXE: dist\X-Checks_FullRun_1.0.59.exe | Double-click dist\X-Checks_FullRun_1.0.59.exe. | Splash screen shows 'X-Check Application v1.0.59 Loading...'. Task selector opens with 'X-Check Application v1.0.59' in title bar and UI label.
FX-02 | Task selector | Whole App | App open at task selector. | Open the task dropdown and count entries. | 6 tasks listed in order: 1. Collect Live X-Checks 2. X-Checks 3. Grouping By 4. Accounting Principles 5. Conditions 6. Full Run
FX-03 | Task selector | Whole App | App open at task selector. | Select each task in turn and confirm the form title. | • Collect Live X-Checks → 'Collect Live X-Checks' • X-Checks → 'X-Check Files' • Grouping By → 'Grouping By Files' • Accounting Principles → 'Accounting Principles Files' • Conditions → 'Conditions Files' • Full Run → 'Full Run — All Strategies'
FX-04 | X-Checks — file fields | Whole App | X-Checks task selected, form open. | Inspect the form fields. | Four fields present: 1. 'FIP File' (.txt) 2. 'X-Checks Publication File' (.xlsx, default sheet: cross checks all) 3. 'GCoA Publication File' (.xlsx, optional) 4. 'Known Exception List' (.xlsx, optional) Two experimental checkboxes unchecked by default. 'Process only differences' present and checked by default.
FX-05 | X-Checks — comparison output | Logic | FIP File: test_data\fixtures\fip_xc.txt X-Checks Publication File: test_data\fixtures\xc_pub.xlsx (sheet: cross checks all) No GCoA. No Known Exception List. 'Process only differences' unchecked. | Load the files above into X-Checks and click Start. | Run completes. Comparison sheet contains exactly 30 rows. Formula Match column values (sorted alphabetically): XC_ABS_FORMULA - Match (Operator 2 set - ABS() wrapping) XC_ALL_MATCH - Match XC_ALL_MISMATCH - MisMatch (formula AND variables wrong) XC_DIFF_EXCLUDED - Not Found (Exclude Z-Core=X, no FIP block) XC_DIFF_GREEN - Match (Type of change=New, green fill - in scope) XC_DIFF_INACTIVE - Not Found (Status=INACTIVE, no FIP block) XC_DIFF_IN_SCOPE - Match (Type of change=Changed, yellow fill - in scope) XC_DIFF_NO_TOC - Not Found (blank Type of change, no FIP block) XC_DIFF_ORANGE - Not Found (Type of change=Removed, excluded) XC_DIFF_YELLOW - Match (Type of change=Changed, yellow fill - in scope) XC_DIFF_YELLOW_CAT - Not Found (Category yellow, no FIP block) XC_EXCL_MATCH - Match (FIP @2A@, EBX excl - Excl cols Match) XC_EXCL_MISMATCH - Match (Formula Match=Match; Excl=MisMatch - see FX-06c) XC_FF_SUFFIX - Match (two accounts - ff suffix) XC_FORMULA_MISMATCH - MisMatch (operator differs <=0 vs >=0; vars same) XC_GTE_OPERATOR - Match (Operator 1 = >=) XC_KEL_MISMATCH - MisMatch (without KEL; annotated when KEL supplied) XC_KEL_NO_MATCH - MisMatch (KEL entry exists but wrong fingerprint) XC_LC_CONST - Match (Shareholders' Equity + non-zero limit - CONST_LC) XC_LC_YTD - Match (Shareholders' Equity - LC_YTD) XC_NONZERO_LIMIT - Match (Limit 1=100 - CONST(100,...)) XC_NOT_IN_EBX - Not Found XC_NOT_IN_FIP - Not Found XC_PCT_FORMAT - Match (% column=X - percentage right-hand side) XC_REORDER_MATCH - MisMatch (known edge case in reorder logic) XC_REX_CORRECTION - Match (FIP uses REX; parser - ToM) XC_SUBTRACT - Match (+ and - operators - subtraction formula) XC_THOUSANDS_CORR - Match (FIP '1.000' stripped to '1000') XC_TOM_CORRECTION - Match (FIP 'TOM' normalised to 'ToM') XC_VARIABLE_MISMATCH - Match (formula matches; FS Account differs) X-Check No. column: green for all-Match rows, red for any MisMatch, orange for Not Found rows.
FX-06 | X-Checks — column-level checks | Logic | FX-05 output open, Comparison sheet. | Check the following specific columns on the rows listed. | a) XC_VARIABLE_MISMATCH: Variables Match = MisMatch; Formula Match = Match. b) XC_FORMULA_MISMATCH: Variables Match = Match (operator differs, account same). c) XC_EXCL_MISMATCH: Formula Match = Match; Formula Match (Excl) = MisMatch (EBX has excl.acc.type=2, FIP has no @2A@ row). d) XC_EXCL_MATCH: Formula Match (Excl) = Match (both EBX and FIP carry excl.acc.type=2).
FX-07 | X-Checks — output structure | Whole App | FX-05 complete. Output workbook open. | Check the sheet tabs. | Workbook contains: 1. Comparison 2. Processing Log
FX-08 | X-Checks — colour coding | Whole App | FX-05 output open, Comparison sheet. | Review fill colours. | Comparison columns: Match → green, MisMatch → red, Not Found → orange. X-Check No. column: green when all 4 columns Match; red when any MisMatch; orange when any Not Found (and no MisMatch).
FX-09 | X-Checks — Known Exception annotation | Logic | Same files as FX-05. Known Exception List: test_data\fixtures\known_exception_list.xlsx (sheet: X-Checks). The KEL contains 2 entries: one correct fingerprint for XC_KEL_MISMATCH, one with wrong fingerprint for XC_KEL_NO_MATCH. | Add the Known Exception List file and run. | Run completes. Progress log shows 'Known exceptions loaded (2)'. XC_KEL_MISMATCH: MisMatch cells → 'MisMatch (Excepted)' with blue fill; X-Check No. cell blue; Known Exception column = 'Test fixture — expected mismatch'. XC_KEL_NO_MATCH: Formula Match remains MisMatch (red); Known Exception blank (fingerprint in KEL does not match the actual row values). All other rows: Known Exception column blank; colours unchanged.
FX-10 | X-Checks — differences mode (X-Check No Selection) | Logic | FIP File: test_data\fixtures\fip_xc.txt X-Checks Publication File: test_data\fixtures\xc_pub.xlsx (sheet: cross checks all) 'Process only differences' checked. | Check 'Process only differences'. Load files and click Start. | Run completes with two outputs: 1. .txt file contains exactly 3 X-Check Nos (Yellow=Changed and Green=New are in scope; Removed=Orange and blank are excluded): XC_DIFF_IN_SCOPE (Type of change=Changed, yellow fill) XC_DIFF_YELLOW (Type of change=Changed, yellow fill) XC_DIFF_GREEN (Type of change=New x-check, green fill) 2. Comparison sheet shows ONLY those 3 rows: XC_DIFF_IN_SCOPE - Match XC_DIFF_YELLOW - Match XC_DIFF_GREEN - Match Absent from Comparison: XC_DIFF_ORANGE (Type of change=Removed - excluded from processing) XC_DIFF_NO_TOC (blank Type of change - not in scope) XC_DIFF_EXCLUDED (Exclude Z-Core=X) XC_DIFF_INACTIVE (Status=INACTIVE) XC_DIFF_YELLOW_CAT (Category cell yellow) All other rows (no Type of change value)
FX-11 | Grouping By — file fields | Whole App | Grouping By task selected, form open. | Inspect the form fields. | Four fields present: 1. 'FIP File (ZQ9_VALFLDGR)' (.xlsx, default sheet: Sheet1) 2. 'X-Checks Publication File' (.xlsx, default sheet: cross checks all) 3. 'Mapping File' (.csv / .txt) 4. 'Known Exception List' (.xlsx, optional)
FX-12 | Grouping By — full comparison output (all 14 rows) | Logic | FIP File (ZQ9_VALFLDGR): fixtures\gb\fip_ZQ9_VALFLDGR.xlsx (sheet: Sheet1) X-Checks Publication File: fixtures\gb\gb_pub.xlsx (sheet: cross checks all) Mapping File: fixtures\gb\gb_mapping.txt 'Process only differences' unchecked. | Load the files above into Grouping By and click Start. | Comparison sheet contains exactly 14 rows. Verify each row by EBX Key and Result: GB_BLANK_VR¦ITEM_A Not in FIP (FIP row has blank ValidRule - dropped during FIP processing) GB_DEDUP¦ITEM_A Not in FIP (first of two identical X-Check rows; no FIP entry) GB_DIFF_GREEN¦ITEM_A Matched (Grouping By cell is green - in scope for diff mode) GB_DIFF_WHITE¦ITEM_A Not in FIP (Grouping By cell is white - out of scope for diff mode) GB_DIFF_YELLOW¦ITEM_A Matched (Grouping By cell is yellow - in scope for diff mode) GB_IGNORE_FIELD¦ITEM_A Not in FIP (FIP field 'GB_IGNORE_FIELD_FIP' maps to 'ignore' - dropped) GB_KEL_MATCH¦ITEM_A Not in FIP (KEL entry with correct fingerprint - annotated) GB_KEL_NO_MATCH¦ITEM_A Not in FIP (KEL entry exists but wrong EBX Key - not annotated) GB_MATCHED¦ITEM_A Matched (standard match: ValidRule=GB_MATCHED maps via GB_FIP_FIELD to ITEM_A) GB_MULTI¦ITEM_A Matched (first of two comma-separated Grouping By values) GB_MULTI¦ITEM_B Not in FIP (second comma-separated value; no FIP entry for ITEM_B) GB_NOT_IN_FIP¦ITEM_A Not in FIP (EBX key present; no matching FIP row) GB_UNMAPPED¦ITEM_A Not in FIP (FIP field 'UNMAPPED_FIELD' not in mapping file - dropped) REF_BASE¦ITEM_A Matched (GB_REF_XC_KEY row: 'Reference X-Check (Condition)'=REF_BASE overrides X-Check No. as base key; FIP has REF_BASE¦ITEM_A) Key logic to verify: - GB_DEDUP second row (Grouping By=ITEM_B) never appears: deduplication keeps only the FIRST row per X-Check No. - GB_IGNORE_FIELD and GB_UNMAPPED test FIP-side filtering: if a field is mapped to 'ignore' or is absent from the mapping file, the FIP row is dropped and the EBX key becomes Not in FIP. - GB_BLANK_VR tests that FIP rows with a blank ValidRule are dropped during processing. - REF_BASE row confirms that the Reference X-Check (Condition) column replaces X-Check No. as the key prefix.
FX-13 | Grouping By — Known Exception annotation | Logic | Same files as FX-12. Known Exception List: fixtures\gb\gb_kel.xlsx (sheet: Grouping By). KEL contains 2 entries: correct fingerprint for GB_KEL_MATCH¦ITEM_A; wrong key for GB_KEL_NO_MATCH. | Add the Known Exception List and run. | GB_KEL_MATCH¦ITEM_A: Result = Not in FIP (unchanged); Known Exception column populated with reason text. GB_KEL_NO_MATCH¦ITEM_A: Result = Not in FIP; Known Exception column BLANK (wrong fingerprint - no match). All other rows: Known Exception column blank.
FX-14 | Grouping By — differences mode (Grouping By cell colour) | Logic | Same files as FX-12. 'Process only differences' checked. | Check 'Process only differences'. Run. | Comparison sheet shows ONLY rows whose Grouping By cell is yellow or green: GB_DIFF_GREEN¦ITEM_A Matched (Grouping By cell green - New x-check) GB_DIFF_YELLOW¦ITEM_A Matched (Grouping By cell yellow - Changed) All other rows absent: their Grouping By cells are plain white (unchanged). Confirm: GB_MATCHED, GB_NOT_IN_FIP, GB_MULTI, REF_BASE etc. do NOT appear.
FX-15 | Grouping By — output structure and colour coding | Whole App | FX-12 complete. Output workbook open. | Check the sheet tabs and Comparison fill colours. | Workbook contains 7 sheets: Mapping File, FIP - Original, FIP - Processed, EBX - Original, EBX - Processed, Comparison, Processing Log. Comparison sheet: 'Matched' rows have green fill; 'Not in FIP' rows have orange fill.
FX-16 | Accounting Principles — file fields | Whole App | Accounting Principles task selected, form open. | Inspect the form fields. | Four fields present: 1. 'Validation Methods File' (.xlsx, default sheet: Validation Methods) 2. 'X-Checks Publication File' (.xlsx, default sheet: cross checks all) 3. 'FIP File (VALMSG)' (.xlsx, sheet: FIP Methods Rules and Condition) 4. 'Known Exception List' (.xlsx, optional)
FX-17 | Accounting Principles — full comparison output (all rows) | Logic | Validation Methods File: fixtures\validation_methods.xlsx (sheet: Validation Methods) X-Checks Publication File: fixtures\ap\ap_pub.xlsx (sheet: cross checks all) FIP File (VALMSG): fixtures\ap\ap_fip_ZQ9_VALMSG.xlsx (sheet: FIP Methods Rules and Condition) Note: fip_ZQ9_VALMSG.xlsx is a raw ZQ9_VALMSG export with no pre-built Key column. 'Process only differences' unchecked. | Load the files above into Accounting Principles and click Start. | Progress log shows 'Built Key column from MK + ValidRule'. Comparison sheet contains 11 rows. Verify each (X-Check No., Event, Expected, FIP, Actual, Match): AP_BOTH_E Stammhaus SLST SFD Both e e Match (Both severity: FIP=e matches actual=e) AP_BOTH_W Stammhaus SLST RFD Both w w Match (Both severity: FIP=w matches actual=w) AP_DIFF_GREEN IFRS New RFD Warning w w Match (event col green - included in full run) AP_DIFF_YELLOW IFRS New RFD Warning w w Match (event col yellow - included in full run) AP_EXCL_ZCORE IFRS New RFD Warning w w Match (Exclude Z-Core=X - excluded only in diff mode) AP_GREY_WINS IFRS New SFD Warning w w Match (black binding column empty; grey binding fires) AP_MATCH_W IFRS New RFD Warning w w Match (FIP letter w = actual w) AP_MISMATCH IFRS New RFD Warning e w MisMatch (FIP letter e != actual w) AP_NOT_SCOPE_INA IFRS New RFD Warning w w Match (INACTIVE - excluded only in diff mode) AP_NOT_SCOPE_TOC IFRS New RFD Warning w w Match (blank Type of change - excluded only in diff mode) AP_YELLOW_CAT IFRS New RFD Warning w w Match (yellow Category - excluded only in diff mode) Rows NOT appearing (skipped entirely): AP_NO_BINDING - FIP sends method V_UNKNOWN_METHOD which has no binding in Validation Methods AP_NO_ACTUAL - IFRS New RFD column is blank; no binding produces a non-empty actual letter AP_DIFF_WHITE - no event column has any fill colour; excluded in diff mode (not relevant here) Key logic to verify: - Both severity rows (AP_BOTH_W, AP_BOTH_E) demonstrate that a single binding accepts either w or e. - AP_GREY_WINS: the black-font binding's event column is blank in ap_pub, so the grey binding fires. Verify AP_GREY_WINS appears with Event=IFRS New SFD (the grey event), not IFRS New RFD. - AP_NO_BINDING row is absent: the method is not in the Validation Methods file at all. - The 'Process only differences' filter rows (EXCL_ZCORE, NOT_SCOPE_INA, etc.) appear here because diff mode is OFF - confirming they are correctly included when the checkbox is unchecked.
FX-18 | Accounting Principles — differences mode (event column colour) | Logic | Same files as FX-17. 'Process only differences' checked. | Check 'Process only differences'. Run. | Comparison sheet shows ONLY rows where at least one validation event column is yellow or green in ap_pub.xlsx: AP_DIFF_GREEN IFRS New RFD Warning w w Match (event col green) AP_DIFF_YELLOW IFRS New RFD Warning w w Match (event col yellow) All other rows absent: AP_MATCH_W, AP_MISMATCH, AP_BOTH_W, AP_BOTH_E etc. have no coloured event columns and are therefore out of scope. Also confirm: AP_NOT_SCOPE_TOC absent (blank Type of change), AP_NOT_SCOPE_INA absent (INACTIVE), AP_EXCL_ZCORE absent (Z-Core=X), AP_YELLOW_CAT absent (yellow Category cell).
FX-19 | Accounting Principles — Known Exception annotation | Logic | Same files as FX-17. Known Exception List: fixtures\ap\ap_kel.xlsx (sheet: Accounting Principles). KEL contains 2 entries: correct 6-column fingerprint for AP_MISMATCH; wrong FIP value for AP_KEL_NO_MATCH. | Add the Known Exception List and run. | AP_MISMATCH: Match = MisMatch (unchanged); Known Exception column populated with reason text. AP_MATCH_W: Known Exception column BLANK (no mismatch - KEL never fires on Match rows). All other rows: Known Exception blank.
FX-20 | Accounting Principles — output structure and colour coding | Whole App | FX-17 complete. Output workbook open. | Check the sheet tabs and Comparison fill colours. | Workbook contains 4 sheets: EBX, FIP, Comparison, Processing Log. Comparison sheet: 'Match' rows have green fill; 'MisMatch' rows have red fill.
FX-21 | Conditions — file fields | Whole App | Conditions task selected, form open. | Inspect the form fields. | Three fields present: 1. 'X-Checks Publication File' (.xlsx, default sheet: cross checks all) 2. 'FIP File (ZQ9_VALMETH)' (.xlsx, default sheet: FIP Conditions) 3. 'Known Exception List' (.xlsx, optional) 'Process only differences' checkbox present and checked by default.
FX-22 | Conditions — full file run (all 15 rows) | Logic | X-Checks Publication File: fixtures\cond\cond_pub.xlsx (sheet: cross checks all) FIP File (ZQ9_VALMETH): fixtures\cond\cond_fip_ZQ9_VALMETH.xlsx (sheet: FIP Conditions) 'Process only differences' unchecked. | Uncheck 'Process only differences'. Load the files and click Start. | Comparison sheet contains exactly 15 rows (one per non-blank condition cell value). Verify each row by EBX Data, FIP Data, and Comparison: COND_APPL_QTRS¦Q1 FIP=COND_APPL_QTRS¦Q1 Matched (Applicable Quarters column) COND_DIFF_GREEN¦RU_NORTH FIP=COND_DIFF_GREEN¦RU_NORTH Matched (Included RUs col, green cell) COND_DIFF_WHITE¦Q1 FIP=(blank) Not Matched (white cell - no colour, not in FIP) COND_DIFF_YELLOW¦Q1 FIP=COND_DIFF_YELLOW¦Q1 Matched (Applicable Quarters col, yellow cell) COND_EXCL_RUS¦RU_SOUTH FIP=COND_EXCL_RUS¦RU_SOUTH Matched (Excluded RUs column) COND_INCL_RUS¦RU_NORTH FIP=COND_INCL_RUS¦RU_NORTH Matched (Included RUs column) COND_KEL_MISMATCH¦Q3 FIP=(blank) Not Matched (KEL annotated - see FX-24) COND_KEL_NO_MATCH¦Q4 FIP=(blank) Not Matched (wrong KEL fingerprint) COND_LIMIT_PCT¦10.5 FIP=COND_LIMIT_PCT¦10.5 Matched (Reference X-Check (Limit, %) column) COND_MULTI_COL¦Q1 FIP=COND_MULTI_COL¦Q1 Matched (multi-col row: Applicable Quarters) COND_MULTI_COL¦RU_IN FIP=COND_MULTI_COL¦RU_IN Matched (multi-col row: Included RUs) COND_MULTI_COL¦RU_OUT FIP=(blank) Not Matched (multi-col row: Excluded RUs - no FIP entry) COND_NOT_MATCHED¦Q2 FIP=(blank) Not Matched (Applicable Quarters value not in FIP) COND_REF_XC¦COND_REF_XC FIP=(blank) Not Matched (Reference X-Check col value itself) COND_REF_XC¦Q1 FIP=COND_REF_XC¦Q1 Matched (Applicable Quarters using ref override) Key logic to verify: - COND_APPL_QTRS, COND_INCL_RUS, COND_EXCL_RUS, COND_LIMIT_PCT each confirm a different one of the 5 condition columns produces output rows. - COND_MULTI_COL produces 3 rows from a single X-Check: one per non-blank condition column. Q1 and RU_IN are in FIP (Matched); RU_OUT is not (Not Matched). - COND_REF_XC row demonstrates the Reference X-Check (Condition) override: The pub row has X-Check No.=COND_REF_XC and Reference X-Check (Condition)=COND_REF_XC. The effective key prefix becomes COND_REF_XC (not the X-Check No. itself). This produces two rows: COND_REF_XC¦COND_REF_XC (col value - Not Matched) and COND_REF_XC¦Q1 (Applicable Quarters with override prefix - Matched). - COND_DIFF_WHITE is Not Matched even in full-file mode: the cell is white but the value Q1 is not in the FIP file for that X-Check No.
FX-23 | Conditions — differences mode (condition cell colour) | Logic | Same files as FX-22. 'Process only differences' checked (default). | Run with 'Process only differences' checked (the default setting). | Comparison sheet shows ONLY rows where the condition cell itself is yellow or green: COND_DIFF_GREEN¦RU_NORTH FIP=COND_DIFF_GREEN¦RU_NORTH Matched (Included RUs cell is green) COND_DIFF_YELLOW¦Q1 FIP=COND_DIFF_YELLOW¦Q1 Matched (Applicable Quarters cell is yellow) All other rows absent - their condition cells are plain white (unchanged). Confirm: COND_MATCHED, COND_NOT_MATCHED, COND_MULTI_COL rows all absent. Note: COND_DIFF_WHITE is also absent because its Applicable Quarters cell has no fill.
FX-24 | Conditions — Known Exception annotation | Logic | Same files as FX-22. Known Exception List: fixtures\cond\cond_kel.xlsx (sheet: Conditions). KEL contains: correct 2-column fingerprint for COND_APPL_QTRS¦Q1 (Matched row); wrong FIP Data fingerprint for COND_INCL_RUS¦RU_NORTH. Note: Not Matched rows have blank FIP Data so cannot be fingerprint-matched by the KEL. | Add the Known Exception List and run with 'Process only differences' unchecked. | COND_APPL_QTRS¦Q1: Comparison = Matched (unchanged); Known Exception column populated with reason text. COND_INCL_RUS¦RU_NORTH: Comparison = Matched; Known Exception BLANK (wrong FIP Data fingerprint). All other rows: Known Exception blank.
FX-25 | Conditions — output structure and colour coding | Whole App | FX-22 complete. Output workbook open. | Check the sheet tabs, FIP Data first column header, and Comparison fill colours. | Workbook contains 4 sheets: Working Sheet, FIP Data, Comparison, Processing Log. FIP Data sheet: first column header is 'Key (Concatenated)'. Comparison sheet: 'Matched' rows have green fill; 'Not Matched' rows have red fill.
FX-26 | Full Run — file fields | Whole App | Full Run task selected, form open. | Count the file fields and verify no duplicates. | All unique fields from every strategy are merged into one form. Fields include: FIP File, X-Checks Publication File, GCoA Publication File, FIP File (ZQ9_VALFLDGR), Mapping File, Validation Methods File, FIP File (VALMSG), FIP File (ZQ9_VALMETH), Known Exception List. No field label appears twice.
FX-27 | Full Run — all strategies | Logic | All fixture files. 'Process only differences' unchecked. • FIP File: test_data\fixtures\fip_xc.txt • X-Checks Publication File: test_data\fixtures\xc_pub.xlsx • FIP File (ZQ9_VALFLDGR): fixtures\gb\fip_ZQ9_VALFLDGR.xlsx • Mapping File: fixtures\gb\gb_mapping.txt • Validation Methods File: test_data\fixtures\validation_methods.xlsx • FIP File (VALMSG): fixtures\ap\ap_fip_ZQ9_VALMSG.xlsx • FIP File (ZQ9_VALMETH): fixtures\cond\cond_fip_ZQ9_VALMETH.xlsx | Load all fixture files into Full Run. Uncheck 'Process only differences'. Click Start. | All four strategies run without error. Combined output contains: XC — Comparison 30 rows (matches FX-05) GB — Comparison 14 rows (matches FX-12) AP — Comparison 11 rows (matches FX-17) Cond — Comparison 15 rows (matches FX-22) Single 'Processing Log' sheet at the end.
FX-28 | Full Run — combined output structure | Whole App | FX-27 complete. Combined output workbook open. | Check all sheet tabs and tab colours. | One workbook with all strategy sheets prefixed by strategy name (e.g. 'XC — Comparison', 'GB — Comparison', 'AP — Comparison', 'Cond — Comparison'). Tabs are colour-coded by strategy. Single 'Processing Log' sheet at the end.
FX-29 | Full Run — abort on strategy failure | Whole App | Full Run form open. | Set an incorrect sheet name for one file, then click Start. | Failing strategy logs a clear error. Full Run aborts immediately — does not continue to the next strategy. 'Return to Form' is available.
FX-30 | Settings — gear menu | Whole App | App open at task selector. | Click the gear button at the bottom-right. | A popup menu appears with at least 'Build Known Exception List...'. No dialog opens directly.
FX-31 | Settings — Known Exception Builder | Whole App | Settings popup open (FX-30). | Click 'Build Known Exception List...'. | Modal dialog opens with: 'Save as' hint text 'Click Browse and select a folder, then type the filename', Browse button, optional comparison import section, 'Open file after building' checkbox (checked by default), Build button.
FX-32 | Settings — build and open KEL | Whole App | Known Exception Builder dialog open. Output folder available. | Click Browse, select a folder, type a filename. Leave 'Open file after building' checked. Click Build. | File created at the chosen path. Dialog closes. File opens in Excel. Contains sheets: X-Checks, Grouping By, Accounting Principles, Conditions, Instructions. Row 2 of each strategy sheet is a guidance row. File carries the 'Internal Use Only' sensitivity label.
FX-33 | Processing Log — content | Whole App | Any completed run. Output workbook open, Processing Log sheet. | Review the log entries. | First entry shows v1.0.59. Log includes: files loaded, strategy steps, output path, expected sensitivity label. All entries have Timestamp, File, Step, Count columns.
FX-34 | Processing Log — output path entry | Whole App | Any completed run. Processing Log sheet open. | Find the 'Output written to' entry. | Entry with File='Output' and Step starting 'Output written to:' is present.
FX-35 | Processing Log — sensitivity label entry | Whole App | Any completed run. Processing Log sheet open. | Find the sensitivity label entry. | Entry with File='Sensitivity' and Step='Expected label: Internal_Use_Only' is present.
FX-36 | Sensitivity label | Whole App | Any completed run. Output .xlsx saved to disk. | Right-click the output file in Explorer, Properties, Details, or open in Excel and check the sensitivity bar. | File carries the 'Internal Use Only' MIP label. Progress dialog shows 'Applied label: Internal_Use_Only'.
FX-37 | Stop / Return to Form | Whole App | Any task started. | Click Stop during processing. | Processing halts. Dialog shows 'Processing halted by user'. 'Return to Form' reopens the form with previously chosen files pre-filled.
FX-38 | Error — wrong sheet name | Whole App | Any task's file-selection form open. | Set a sheet name to 'does_not_exist', then click Start. | Run aborts with a clear error identifying the missing sheet. App returns to form — does not crash.
FX-39 | Error — missing required file | Whole App | Any task's file-selection form open. | Click Start without selecting any required files. | Start does not begin processing. Form indicates missing required fields.

## Sign-off
Fixture-Based UAT v1.0.59 — Sign-off
Outcome | All in-scope cases passed (or any failure logged and triaged)?
Tester (name)
Tester (role)
Test start date
Test end date
Pass / Fail
Failures (count)
Notes
Approver (name)
Approver (role)
Approval date