## Overview
Fixture-Based UAT v1.0.34 — Test Plan
Version: v1.0.34 ¦ 8 Logic cases ¦ 28 Whole App cases
Purpose | Standalone UAT for X-Checks Full Application v1.0.34 using the minimal fixture files in test_data\fixtures\. Covers all strategies, UI, output structure, colour coding, sensitivity labelling, and error handling. Test cases are categorised: Logic (8 cases) — verifies row-level comparison output. Run after every code change to confirm strategy logic is correct. Whole App (28 cases) — verifies UI, structure, labelling, error handling. Run for full release sign-off.
Fixture files | All in test_data\fixtures\: xc_pub.xlsx — shared EBX publication (all strategies) fip_xc.txt — FIP X-Checks text fip_ZQ9_VALFLDGR.xlsx — FIP Grouping By mapping.txt — Grouping By mapping validation_methods.xlsx — AP Validation Methods (real reference file) fip_ZQ9_VALMSG.xlsx — FIP AP (raw ZQ9_VALMSG) fip_ZQ9_VALMETH.xlsx — FIP Conditions (raw ZQ9_VALMETH) Regenerate (except validation_methods.xlsx) with: python test_data/generate_test_fixtures.py
Test executable | dist\X-Checks_FullRun_1.0.34.exe
Pre-conditions | 1) EXE present in dist\. 2) No fixture files open in Excel. 3) An output folder is available and writable. 4) MIP client installed (for sensitivity-label checks). 5) 'Process only differences' unchecked unless the test case specifies otherwise.

## Test Cases
Fixture-Based UAT v1.0.34 — Test Cases
Test Type: Logic = verify comparison output logic Whole App = verify UI, structure, labelling, error handling
ID | Area | Test Type | Files / Setup | Steps | Expected Result | Actual Result | Pass / Fail | Tester | Date
FX-01 | Launch & version | Whole App | Production EXE: dist\X-Checks_FullRun_1.0.34.exe | Double-click dist\X-Checks_FullRun_1.0.34.exe. | Splash screen shows 'X-Check Application v1.0.34 Loading...'. Task selector opens with 'X-Check Application v1.0.34' in title bar and UI label.
FX-02 | Task selector | Whole App | App open at task selector. | Open the task dropdown and count entries. | 6 tasks listed in order: 1. Collect Live X-Checks 2. X-Checks 3. Grouping By 4. Accounting Principles 5. Conditions 6. Full Run
FX-03 | Task selector | Whole App | App open at task selector. | Select each task in turn and confirm the form title. | • Collect Live X-Checks → 'Collect Live X-Checks' • X-Checks → 'X-Check Files' • Grouping By → 'Grouping By Files' • Accounting Principles → 'Accounting Principles Files' • Conditions → 'Conditions Files' • Full Run → 'Full Run — All Strategies'
FX-04 | X-Checks — file fields | Whole App | X-Checks task selected, form open. | Inspect the form fields. | Four fields present: 1. 'FIP File' (.txt) 2. 'X-Checks Publication File' (.xlsx, default sheet: cross checks all) 3. 'GCoA Publication File' (.xlsx, optional) 4. 'Known Exception List' (.xlsx, optional) Two experimental checkboxes unchecked by default. 'Process only differences' present and checked by default.
FX-05 | X-Checks — comparison output | Logic | FIP File: test_data\fixtures\fip_xc.txt X-Checks Publication File: test_data\fixtures\xc_pub.xlsx (sheet: cross checks all) No GCoA. No Known Exception List. 'Process only differences' unchecked. | Load the files above into X-Checks and click Start. | Run completes. Comparison sheet contains exactly 8 rows. Formula Match column values: XC_ALL_MATCH → Match XC_FORMULA_MISMATCH → MisMatch XC_NOT_IN_EBX → Not Found XC_NOT_IN_FIP → Not Found XC_REORDER_MATCH → MisMatch (known edge case in reorder logic) XC_THOUSANDS_CORR → Match (FIP '1.000' stripped to '1000') XC_TOM_CORRECTION → Match (FIP 'TOM' normalised to 'ToM') XC_VARIABLE_MISMATCH → Match
FX-06 | X-Checks — Variables Match | Logic | FX-05 output open, Comparison sheet. | Check the Variables Match column. | XC_VARIABLE_MISMATCH: Variables Match = MisMatch (formula matched but FS Account differed). All other rows: Variables Match mirrors Formula Match.
FX-07 | X-Checks — output structure | Whole App | FX-05 complete. Output workbook open. | Check the sheet tabs. | Workbook contains: 1. Comparison 2. Processing Log
FX-08 | X-Checks — colour coding | Whole App | FX-05 output open, Comparison sheet. | Review fill colours in the Formula Match column. | Match rows → green fill. MisMatch rows → red fill. Not Found rows → orange fill.
FX-09 | X-Checks — Known Exception annotation | Logic | Same files as FX-05. Known Exception List: test_data\20260721 Known Exception List.xlsx (sheet: X-Checks). | Add the Known Exception List and run. | Run completes. Progress log references the Known Exception List. Any row whose fingerprint matches an exception entry has a 'Known Exception' column populated with the Reason text and a blue cell fill.
FX-10 | Grouping By — file fields | Whole App | Grouping By task selected, form open. | Inspect the form fields. | Four fields present: 1. 'FIP File (ZQ9_VALFLDGR)' (.xlsx, default sheet: Sheet1) 2. 'X-Checks Publication File' (.xlsx, default sheet: cross checks all) 3. 'Mapping File' (.csv / .txt) 4. 'Known Exception List' (.xlsx, optional)
FX-11 | Grouping By — comparison output | Logic | FIP File (ZQ9_VALFLDGR): test_data\fixtures\fip_ZQ9_VALFLDGR.xlsx (sheet: Sheet1) X-Checks Publication File: test_data\fixtures\xc_pub.xlsx (sheet: cross checks all) Mapping File: test_data\fixtures\mapping.txt | Load the files above into Grouping By and click Start. | Run completes. Comparison sheet contains exactly 2 rows: GB_MATCHED¦GB_GROUPING_ITEM → Matched GB_NOT_IN_FIP¦GB_GROUPING_ITEM → Not in FIP
FX-12 | Grouping By — output structure | Whole App | FX-11 complete. Output workbook open. | Check the sheet tabs. | Workbook contains: 1. Mapping File 2. FIP - Original 3. FIP - Processed 4. EBX - Original 5. EBX - Processed 6. Comparison 7. Processing Log
FX-13 | Grouping By — colour coding | Whole App | FX-11 output open, Comparison sheet. | Review the Result column fill colours. | 'Matched' → green fill. 'Not in FIP' → orange fill.
FX-14 | Accounting Principles — file fields | Whole App | Accounting Principles task selected, form open. | Inspect the form fields. | Four fields present: 1. 'Validation Methods File' (.xlsx, default sheet: Validation Methods) 2. 'X-Checks Publication File' (.xlsx, default sheet: cross checks all) 3. 'FIP File (VALMSG)' (.xlsx, sheet: FIP Methods Rules and Condition) 4. 'Known Exception List' (.xlsx, optional)
FX-15 | Accounting Principles — Key column built from raw VALMSG | Logic | Validation Methods File: test_data\fixtures\validation_methods.xlsx (sheet: Validation Methods) X-Checks Publication File: test_data\fixtures\xc_pub.xlsx (sheet: cross checks all) FIP File (VALMSG): test_data\fixtures\fip_ZQ9_VALMSG.xlsx (sheet: FIP Methods Rules and Condition) Note: fip_ZQ9_VALMSG.xlsx is a raw ZQ9_VALMSG export — no pre-built Key column. | Load the files above into Accounting Principles and click Start. | Run completes. Progress log shows 'Built Key column from MK + ValidRule'. Comparison sheet contains exactly 2 rows: AP_MATCH Event=IFRS New RFD FIP=w Actual=w → Match AP_MISMATCH Event=IFRS New RFD FIP=e Actual=w → MisMatch
FX-16 | Accounting Principles — output structure | Whole App | FX-15 complete. Output workbook open. | Check the sheet tabs. | Workbook contains: 1. EBX 2. FIP 3. Comparison 4. Processing Log
FX-17 | Accounting Principles — colour coding | Whole App | FX-15 output open, Comparison sheet. | Review the Match column fill colours. | 'Match' → green fill. 'MisMatch' → red fill.
FX-18 | Conditions — file fields | Whole App | Conditions task selected, form open. | Inspect the form fields. | Three fields present: 1. 'X-Checks Publication File' (.xlsx, default sheet: cross checks all) 2. 'FIP File (ZQ9_VALMETH)' (.xlsx, default sheet: FIP Conditions) 3. 'Known Exception List' (.xlsx, optional) 'Process only differences' checkbox present and checked by default.
FX-19 | Conditions — full file run | Logic | X-Checks Publication File: test_data\fixtures\xc_pub.xlsx (sheet: cross checks all) FIP File (ZQ9_VALMETH): test_data\fixtures\fip_ZQ9_VALMETH.xlsx (sheet: FIP Conditions) 'Process only differences' unchecked. | Uncheck 'Process only differences'. Load the files and click Start. | Run completes. Comparison sheet contains exactly 4 rows: COND_MATCHED¦Q1 FIP Data=COND_MATCHED¦Q1 → Matched COND_NOT_MATCHED¦Q2 FIP Data=(blank) → Not Matched COND_BASE¦COND_BASE FIP Data=(blank) → Not Matched COND_BASE¦Q1 FIP Data=COND_BASE¦Q1 → Matched Note: COND_BASE¦COND_BASE is expected — the 'Reference X-Check (Condition)' column is itself one of the 5 condition columns. COND_BASE¦Q1 confirms the key-prefix override works correctly.
FX-20 | Conditions — differences only | Logic | Same files as FX-19. 'Process only differences' checked (default). | Run with 'Process only differences' checked (default). | Comparison sheet is empty (0 data rows). The fixture EBX rows have no yellow or green cell fill, so no rows are collected in differences mode.
FX-21 | Conditions — output structure | Whole App | FX-19 complete. Output workbook open. | Check the sheet tabs and first column header of the FIP Data sheet. | Workbook contains: 1. Working Sheet 2. FIP Data (first column header: 'Key (Concatenated)') 3. Comparison 4. Processing Log
FX-22 | Conditions — colour coding | Whole App | FX-19 output open, Comparison sheet. | Review the Comparison column fill colours. | 'Matched' → green fill. 'Not Matched' → red fill.
FX-23 | Full Run — file fields | Whole App | Full Run task selected, form open. | Count the file fields and verify no duplicates. | All unique fields from every strategy are merged into one form. Fields include: FIP File, X-Checks Publication File, GCoA Publication File, FIP File (ZQ9_VALFLDGR), Mapping File, Validation Methods File, FIP File (VALMSG), FIP File (ZQ9_VALMETH), Known Exception List. No field label appears twice.
FX-24 | Full Run — all strategies | Logic | All fixture files. 'Process only differences' unchecked. • FIP File: test_data\fixtures\fip_xc.txt • X-Checks Publication File: test_data\fixtures\xc_pub.xlsx • FIP File (ZQ9_VALFLDGR): test_data\fixtures\fip_ZQ9_VALFLDGR.xlsx • Mapping File: test_data\fixtures\mapping.txt • Validation Methods File: test_data\fixtures\validation_methods.xlsx • FIP File (VALMSG): test_data\fixtures\fip_ZQ9_VALMSG.xlsx • FIP File (ZQ9_VALMETH): test_data\fixtures\fip_ZQ9_VALMETH.xlsx | Load all fixture files into Full Run. Uncheck 'Process only differences'. Click Start. | All four strategies run without error. Combined output contains: XC — Comparison 8 rows GB — Comparison 2 rows AP — Comparison 2 rows Cond — Comparison 4 rows Row counts and values match the individual strategy results in FX-05, FX-11, FX-15, FX-19.
FX-25 | Full Run — combined output structure | Whole App | FX-24 complete. Combined output workbook open. | Check all sheet tabs and tab colours. | One workbook with all strategy sheets prefixed by strategy name (e.g. 'XC — Comparison', 'GB — Comparison', 'AP — Comparison', 'Cond — Comparison'). Tabs are colour-coded by strategy. Single 'Processing Log' sheet at the end.
FX-26 | Full Run — abort on strategy failure | Whole App | Full Run form open. | Set an incorrect sheet name for one file, then click Start. | Failing strategy logs a clear error. Full Run aborts immediately — does not continue to the next strategy. 'Return to Form' is available.
FX-27 | Settings — gear menu | Whole App | App open at task selector. | Click the ⚙ gear button at the bottom-right. | A popup menu appears with at least 'Build Known Exception List…'. No dialog opens directly.
FX-28 | Settings — Known Exception Builder | Whole App | Settings popup open (FX-27). | Click 'Build Known Exception List…'. | Modal dialog opens with: 'Save as' hint text 'Click Browse and select a folder, then type the filename', Browse button, optional comparison import section, 'Open file after building' checkbox (checked by default), Build button.
FX-29 | Settings — build and open KEL | Whole App | Known Exception Builder dialog open. Output folder available. | Click Browse, select a folder, type a filename. Leave 'Open file after building' checked. Click Build. | File created at the chosen path. Dialog closes. File opens in Excel. Contains sheets: X-Checks, Grouping By, Accounting Principles, Conditions, Instructions. Row 2 of each strategy sheet is a guidance row. File carries the 'Internal Use Only' sensitivity label.
FX-30 | Processing Log — content | Whole App | Any completed run. Output workbook open, Processing Log sheet. | Review the log entries. | First entry shows v1.0.34. Log includes: files loaded, strategy steps, output path, expected sensitivity label. All entries have Timestamp, File, Step, Count columns.
FX-31 | Processing Log — output path entry | Whole App | Any completed run. Processing Log sheet open. | Find the 'Output written to' entry. | Entry with File='Output' and Step starting 'Output written to:' is present.
FX-32 | Processing Log — sensitivity label entry | Whole App | Any completed run. Processing Log sheet open. | Find the sensitivity label entry. | Entry with File='Sensitivity' and Step='Expected label: Internal_Use_Only' is present.
FX-33 | Sensitivity label | Whole App | Any completed run. Output .xlsx saved to disk. | Right-click the output file in Explorer → Properties → Details, or open in Excel and check the sensitivity bar. | File carries the 'Internal Use Only' MIP label. Progress dialog shows 'Applied label: Internal_Use_Only'.
FX-34 | Stop / Return to Form | Whole App | Any task started. | Click Stop during processing. | Processing halts. Dialog shows 'Processing halted by user'. 'Return to Form' reopens the form with previously chosen files pre-filled.
FX-35 | Error — wrong sheet name | Whole App | Any task's file-selection form open. | Set a sheet name to 'does_not_exist', then click Start. | Run aborts with a clear error identifying the missing sheet. App returns to form — does not crash.
FX-36 | Error — missing required file | Whole App | Any task's file-selection form open. | Click Start without selecting any required files. | Start does not begin processing. Form indicates missing required fields.

## Sign-off
Fixture-Based UAT v1.0.34 — Sign-off
Outcome | All in-scope cases passed (or any failure logged and triaged)?
Tester (name)
Tester (role)
Test start date
Test end date
Pass / Fail
Failures (count)
Notes
Approver (name)
Approver (role)
Approval date